## Month 1 Daily Schedule
OJCOMMERCE — MONTH 1 DAILY OUTREACH SCHEDULE
Target: 4 backlinks ¦ ~80 outreach emails ¦ 4 emails/day (Mon-Fri) ¦ Weeks 1-2: Setup & Research ¦ Weeks 3-4: Active Outreach
Month 1 Target: 4 Links |  |  | Emails Required: ~80 |  |  | Daily Rate: 4 emails/day
Day | Date | Day of Week | Time Block | Task Type | Specific Actions | Emails to Send | Follow-ups | Notes / Tips
WEEK 1: SETUP, RESEARCH & AUDIT
1 | Day 1 | Monday | 9AM-12PM 1PM-3PM | SETUP & AUDIT | 1. Run OJCommerce through Ahrefs 2. Document current DR, backlinks, referring domains 3. Set up outreach tracking spreadsheet 4. Set up email templates | 0 | 0 | No emails yet — foundation day. Get all tools and templates ready.
2 | Day 2 | Tuesday | 9AM-12PM 1PM-3PM | COMPETITOR RESEARCH | 1. Run One Stop Bedroom through Ahrefs 2. Run Rooms To Go through Ahrefs 3. Run Bed Bath & Beyond through Ahrefs 4. Document all competitor data | 0 | 0 | REPORT TO ALKESH: Tuesday update #1 — share audit progress.
3 | Day 3 | Wednesday | 9AM-12PM 1PM-3PM | COMPETITOR RESEARCH | 1. Run Wayfair through Ahrefs 2. Run Ashley Furniture through Ahrefs 3. Run Backlink Gap analysis (all 5 vs OJCommerce) 4. Identify top 20 gap opportunities | 0 | 0 | Focus on finding DR 60+ sites that link to competitors but NOT OJCommerce.
4 | Day 4 | Thursday | 9AM-12PM 1PM-3PM | PROSPECT LIST BUILDING | 1. Research 25 potential target websites 2. Verify each: DR 60+, real US traffic, furniture niche 3. Find contact emails using Hunter.io 4. Add to prospect spreadsheet | 0 | 0 | Quality over quantity. Only add sites that meet ALL criteria.
5 | Day 5 | Friday | 9AM-12PM 1PM-3PM | PROSPECT LIST + FIRST EMAILS | 1. Research 15 more prospect websites 2. Finalize Week 1 prospect list (40 prospects) 3. Send FIRST 4 outreach emails to best prospects 4. Prepare Week 2 plan | 4 | 0 | REPORT TO ALKESH: Friday update #1 — share audit results, competitor data, prospect list.
WEEKEND
WEEK 2: OUTREACH BEGINS
6 | Day 6 | Monday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + HARO | 1. Check for responses from Friday emails 2. Sign up for HARO (connectively.us) 3. Send 4 NEW outreach emails (guest post pitches) 4. Respond to 2 HARO queries | 4 | 0 | Start HARO early — responses take time but yield high-DR links.
7 | Day 7 | Tuesday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + FOLLOW-UP | 1. Send 4 NEW outreach emails 2. Send Follow-up #1 to Day 5 emails (3 days later) 3. Respond to any HARO queries 4. Research 5 new prospects | 4 | 4 | REPORT TO ALKESH: Tuesday update #2 — outreach started, X emails sent.
8 | Day 8 | Wednesday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + CONTENT | 1. Send 4 NEW outreach emails 2. If anyone said YES — start writing article 3. Respond to HARO queries 4. Research 5 new prospects | 4 | 0 | If you get a YES, prioritize writing content immediately.
9 | Day 9 | Thursday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + FOLLOW-UP | 1. Send 4 NEW outreach emails 2. Send Follow-up #1 to Monday emails 3. Continue writing content for any YES responses 4. Respond to HARO | 4 | 4 | Follow-up emails get 30% more responses than first emails.
10 | Day 10 | Friday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + REPORT | 1. Send 4 NEW outreach emails 2. Send Follow-up #1 to Tuesday emails 3. Submit any completed articles 4. Prepare weekly report for Alkesh | 4 | 4 | REPORT TO ALKESH: Friday update #2 — emails sent, responses received, content status.
WEEKEND
WEEK 3: SCALE OUTREACH
11 | Day 11 | Monday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + FOLLOW-UP | 1. Send 4 NEW outreach emails 2. Send Follow-up #2 (final) to Day 5 emails 3. Send Follow-up #1 to Wednesday emails 4. HARO responses | 4 | 4-8 | Week 3 is when first links typically go live.
12 | Day 12 | Tuesday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + CONTENT | 1. Send 4 NEW outreach emails 2. Write/submit articles for YES responses 3. Follow-up on pending submissions 4. HARO responses | 4 | 2-4 | REPORT TO ALKESH: Tuesday update #3 — first links may be live!
13 | Day 13 | Wednesday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + VERIFY | 1. Send 4 NEW outreach emails 2. Verify any published links (check dofollow) 3. Document acquired links in backlink log 4. Follow-ups | 4 | 2-4 | Every published link must be verified and documented immediately.
14 | Day 14 | Thursday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + FOLLOW-UP | 1. Send 4 NEW outreach emails 2. Send follow-ups to previous week's emails 3. Continue content creation for YES responses 4. HARO | 4 | 4-6 | By now you should have 1-2 links acquired or in pipeline.
15 | Day 15 | Friday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + REPORT | 1. Send 4 NEW outreach emails 2. Final follow-ups on old prospects 3. Update backlink log 4. Weekly report to Alkesh | 4 | 2-4 | REPORT TO ALKESH: Friday update #3 — links acquired, pipeline status.
WEEKEND
WEEK 4: CLOSE & DELIVER
16 | Day 16 | Monday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + CLOSE | 1. Send 4 NEW outreach emails 2. Follow up on all pending YES responses 3. Push for article publication on accepted posts 4. HARO responses | 4 | 4-6 | Push to close any pending placements before month end.
17 | Day 17 | Tuesday | 9AM-10AM 10AM-12PM 1PM-3PM | OUTREACH + CONTENT | 1. Send 4 NEW outreach emails 2. Submit final articles 3. Verify all live links 4. Update tracking spreadsheet | 4 | 2-4 | REPORT TO ALKESH: Tuesday update #4 — final week push.
18 | Day 18 | Wednesday | 9AM-12PM 1PM-3PM | CONTENT + VERIFY | 1. Send 2 NEW outreach emails 2. Focus on getting pending articles published 3. Verify all links 4. Build Month 2 prospect list | 2 | 2-4 | Start building Month 2 pipeline while closing Month 1.
19 | Day 19 | Thursday | 9AM-12PM 1PM-3PM | FINAL PUSH | 1. Send 2 NEW outreach emails 2. Final follow-ups on everything pending 3. Verify and document all links 4. Prepare monthly report | 2 | 4-6 | Last push to hit 4-link target.
20 | Day 20 | Friday | 9AM-12PM 1PM-3PM | MONTHLY REPORT | 1. Finalize all link verifications 2. Complete Month 1 backlink report 3. Referral traffic snapshot 4. Present Month 2 plan to Alkesh | 0 | 0 | REPORT TO ALKESH: Full Month 1 Report — links acquired, traffic data, Month 2 strategy.
MONTH 1 TOTALS
| Total Working Days |  |  |  | 20 days
| Total NEW Outreach Emails |  |  |  | ~72-80 emails
| Total Follow-up Emails |  |  |  | ~40-55 follow-ups
| Total Emails Sent (all types) |  |  |  | ~120-135 emails
| HARO Responses |  |  |  | ~15-20 responses
| Expected YES Responses |  |  |  | 4-8 (5-10% of outreach)
| Target Links Acquired |  |  |  | 4 backlinks (DR 60+)
| Articles Written |  |  |  | 4-6 guest posts
| Reports to Alkesh |  |  |  | 8 reports (2x per week)

## Daily Time Blocks
IDEAL DAILY SCHEDULE — OUTREACH TIME BLOCKS
Best time to send outreach emails: Tuesday-Thursday, 9-11 AM recipient's time zone (EST for US)
Time Block | Activity | Details
9:00 - 9:30 AM | CHECK INBOX & RESPOND | 1. Check for replies from previous outreach 2. Respond to YES replies immediately 3. Handle any editor questions or revision requests 4. Check HARO daily digest email
9:30 - 10:30 AM | SEND NEW OUTREACH EMAILS | 1. Send 4 personalized outreach emails 2. Each email should be customized (not copy-paste) 3. Reference specific article on their site 4. Use email templates but personalize 20-30%
10:30 - 11:00 AM | SEND FOLLOW-UPS | 1. Follow up on emails sent 3-4 days ago (Follow-up #1) 2. Follow up on emails sent 10 days ago (Follow-up #2 — final) 3. Update tracking spreadsheet with status
11:00 - 12:00 PM | CONTENT WRITING | 1. Write guest post articles for approved placements 2. 1,500-2,000 words per article 3. Include natural OJCommerce backlink 4. Professional, trust-driven, value-focused tone
12:00 - 1:00 PM | LUNCH BREAK | Take a break!
1:00 - 2:00 PM | PROSPECT RESEARCH | 1. Find 5 new potential target websites 2. Verify DR 60+, US traffic, furniture niche 3. Find contact emails via Hunter.io 4. Add to prospect spreadsheet
2:00 - 2:30 PM | HARO RESPONSES | 1. Check afternoon HARO digest 2. Respond to 1-2 relevant journalist queries 3. Provide expert quotes as OJCommerce representative
2:30 - 3:00 PM | TRACK & DOCUMENT | 1. Update outreach tracking spreadsheet 2. Verify any newly published links 3. Document acquired links in backlink log 4. Prepare notes for Alkesh's report (if report day)
3:00 - 3:30 PM | REPORTING (Tue & Fri only) | 1. Tuesday: Send mid-week update to Alkesh 2. Friday: Send end-of-week update to Alkesh 3. Include: emails sent, responses, links acquired, pipeline

## 12-Month Weekly Overview
OJCOMMERCE — 12-MONTH WEEKLY OUTREACH OVERVIEW
Month | Week | New Emails /Week | Follow-ups /Week | HARO Responses | Total Emails /Week | Links Target | Cumulative Links | Referral Traffic % | Key Focus
MONTH 1: FOUNDATION (Target: 4 links)
M1 | Week 1 | 4 | 0 | 0 | 4 | 0 | 0 | 0.28% | Setup, audit, competitor research, prospect list
M1 | Week 2 | 20 | 4 | 4 | 28 | 0-1 | 0-1 | 0.28% | Active outreach begins, HARO signup
M1 | Week 3 | 20 | 12 | 4 | 36 | 1-2 | 1-3 | 0.30% | Scale outreach, first YES responses, content writing
M1 | Week 4 | 12 | 10 | 4 | 26 | 1-2 | 2-4 | 0.43% | Close placements, verify links, monthly report
MONTH 2: SCALE (Target: 6 links)
M2 | Week 5 | 24 | 8 | 4 | 36 | 1-2 | 5-6 | 0.50% | New prospect batch, continued outreach
M2 | Week 6 | 24 | 12 | 4 | 40 | 1-2 | 6-8 | 0.55% | Scale up, follow-ups from Week 5
M2 | Week 7 | 24 | 12 | 4 | 40 | 1-2 | 7-9 | 0.60% | Content creation, link verification
M2 | Week 8 | 20 | 10 | 3 | 33 | 1-2 | 8-10 | 0.73% | Close Month 2, monthly report
MONTH 3: MOMENTUM (Target: 8 links)
M3 | Week 9 | 30 | 10 | 5 | 45 | 2 | 10-12 | 0.85% | Increased volume, Tier 2 publications targeted
M3 | Week 10 | 30 | 14 | 5 | 49 | 2 | 12-14 | 0.95% | Digital PR pitches, HARO acceleration
M3 | Week 11 | 30 | 14 | 5 | 49 | 2 | 14-16 | 1.10% | Content production at scale
M3 | Week 12 | 24 | 12 | 4 | 40 | 2 | 16-18 | 1.23% | Close Month 3, quarterly review
MONTHS 4-6: OPTIMIZE (Target: 10-12 links/month)
M4-6 | Weeks 13-24 | 30-40/wk | 14-18/wk | 5-6/wk | 50-60/wk | 2-3/wk | 28-50 | 1.96%-3.93% | Consistent output, higher DR targets, digital PR
MONTHS 7-9: ACCELERATE (Target: 12-14 links/month)
M7-9 | Weeks 25-36 | 35-45/wk | 16-20/wk | 6-8/wk | 55-70/wk | 3-4/wk | 62-88 | 4.99%-7.20% | 5% TARGET HIT (Month 7). Premium DR 70-80+ links. Scale everything.
MONTHS 10-12: MAXIMIZE (Target: 14-15 links/month)
M10-12 | Weeks 37-48 | 40-50/wk | 18-22/wk | 6-8/wk | 65-80/wk | 3-4/wk | 102-131 | 8.35%-9.99% | 10% STRETCH TARGET (Month 12). Elite placements. 131 total links.

## Outreach Tracker
OUTREACH EMAIL TRACKER — LOG EVERY EMAIL HERE
Track every outreach email, follow-up, response, and result. Update daily.
# | Date Sent | Target Website | Contact Person & Email | DR | Email Type | Status | Follow-up #1 Date | Follow-up #2 Date | Response Date | Result | Notes
1 | Mar 2, 2026 | homedesignblog.com | sarah@homedesignblog.com | 65 | Guest Post | YES - Writing | Mar 5 | N/A | Mar 6 | LINK ACQUIRED | Article published Mar 15
2 | Mar 2, 2026 | furnituretips.com | editor@furnituretips.com | 62 | Guest Post | No Reply | Mar 5 | Mar 12 | - | MOVED ON | No response after 2 follow-ups
3 | Mar 2, 2026 | interiordesignmag.com | james@interiordesignmag.com | 71 | Guest Post | YES - Pending | Mar 5 | N/A | Mar 7 | IN PROGRESS | Article submitted, waiting for publish
4 | Mar 2, 2026 | homedecorinspo.com | info@homedecorinspo.com | 58 | Guest Post | REJECTED | - | - | - | BELOW DR 60 | DR too low — shouldn't have sent
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100